## Tracker
ID | Reviewer comment (short) | Severity | Type | Tasks (do in this order) | Deliverable / where it goes | Depends on | Phase | Status | % done | What is done so far / blockers
1 | Calibration on non-converged mesh (802k vs 18.9M) | Major | Compute + text | 1) Re-derive coarse->fine correction on v4 (fine runs hmin0.25, 4+ parameter pairs, film mode). 2) Calibrate on coarse + correction AND on one finer mesh; report both parameter sets. 3) Quantify optimum / validation RMSE vs mesh (3 levels). 4) Re-run mesh-convergence study at FINAL parameters (state whether pre- or post-calibration). 5) Add table: mesh used for every result in Figs 3-8. | New SI table 'mesh used per figure'; mesh-convergence figure at final parameters; text in Methods | A (frozen v4 film model) | A | Draft done | 80 | D:\PhD (Monash Uni)\PhD Project\Stage 2\Paper 2\Metamaterials deisgn using ML Nature Paper\HPC model\pod_surrogate_v3\Meshes\Disc\Correlation_Study Update 09-Oct: SI S8: mesh-correction figure added (Figure S9, L2 vs L6, r = 0.9986, L2 = 1.355846 x L6) with text; Table S15 (coarse/fine pairs, constants) still a placeholder. Correction not yet re-derived on v4 film runs.
2 | Dimensional / stoichiometric consistency of Eqs 7-17 | Major | Text + compute | 1) Insert molar-basis Eqs 7-14 and units table (Table S-U) in manuscript/SI. 2) Fix Table 1 (delete [Zn]sat, add delta_f, reconcile rho_film 3.998 vs 5.606, tau 120 vs 2.0, diffusivities). 3) Validate OH- equation (or drop pH). 4) Global balance table (Zn solid/dissolved/film, O2 supplied/consumed, charge) for final model at 24/168/336/672 h. 5) Medium replacement: state 'none' or implement 48 h reset (see 8). | Rewritten Methods section; Table S-U; Table S-B (balance); Table 1 corrected | A, 10 | B | Draft done | 80 | Draft Word file exists (Manuscript_model_section_v4_DRAFT.docx). Balance done for v4 volumetric film (Zn within 6-16 %, stoich 1.03-1.18) and old code (376-504x). Needs rerun on surface-film model; OH- unvalidated. Update 09-Oct: Manuscript: Eqs 7, 9, 10, 14 rewritten with j_ORR = k_ORR C_O2¦Gamma [mol mm-2 h-1]; F defined as molar (ZnO-equivalent) and Fmax = rho_film(1-eps)/M_film; kappa(F) removed (volumetric-film code); Table 1 C_Cl0, C_O2,0 now molar; units table S13 in SI. Table S14 (balance) still a placeholder; Table 1 delta_f / rho_film reconciliation not applied because film stays volumetric.
3 | Hard-minimum velocity rule needs justification | Major | Text (+ 1 small check) | 1) Write derivation from the interfacial O2 balance: Robin condition = series (harmonic) combination of reaction and transport. 2) Run a planar test: numerical v vs analytic series formula (small case). 3) Replace Table S1 / Fig S1 (rule A-D) with the historical comparison or remove; delete 'two regime transitions' sentence. 4) Short reply: no switching surfaces remain, rules A-D no longer part of model. | SI Section S1 rewritten; response paragraph | 2 | D | Draft done | 85 | Min() removed in v4 (mode 2, v = v_ORR with Robin O2 condition). Argument drafted in chat; derivation and planar check not yet written. Update 09-Oct: SI S1 derivation + Table S1 (flux regimes) written; manuscript Level Set section rewritten (novelty for Zn models, no velocity cap, Robin wording replaced by interface-localized sink). Planar numerical test not yet run.
4 | Calibration / validation / consistency-check terminology; Zn2+ & pH metrics | Moderate | Compute + text | 1) Apply the 5-term terminology throughout (calibration, independent validation, out-of-objective check, predictive case study, not validation). 2) Compute RMSE, NRMSE, bias and residuals for Zn2+ and pH over all time points. 3) Do not call the 44 % Zn2+ gap 'reproduction of the overall evolution'. 4) Decide whether pH stays (needs validated OH- equation). | Table in SI with metrics; text edits in Results | A, 2 (OH-) | B | Not started | 0
5 | Parameter identifiability not established | Major | Compute + text | 1) 1-D profiles for k_ORR, k_f, k_d (profile RMSE). 2) Repeated BO with a second seed on the film model. 3) GP cross-validation error. 4) Show equal-RMSE parameter sets with different O2 / Zn2+ / film predictions. 5) Consider adding Zn2+ (or pH) to the objective. 6) State clearly that only k_ORR is well determined if that remains true. | New SI figure (profiles, trade-offs); updated Table S10 | A | B | In progress | 25 | No-film BO (phases 1-2) shows only k_ORR (about 25) identifiable; film-mode phase 1 (16 round-number runs) is running. Update 09-Oct: Fig S4 rebuilt from the 32-evaluation BO (trajectories + RMSE surfaces, log axes); BO table of all 32 evaluations in the chat/CSV; Morris ranges in Table S5 updated to v4 values (k_f 3e4-3e6, k_d 1e6-1e9, k_ORR 10-200). Not done: second-seed repeat, 1-D profiles, GP cross-validation, Morris rerun, Tables S9/S10.
6 | Uncertainty analysis too narrow | Moderate | Compute + text | 1) Show interval convergence vs ensemble size (50 vs more draws). 2) Add measurement SD, O2 and diffusivity, film porosity/tortuosity, mesh/time-step uncertainty to a predictive interval. 3) Plot experimental mean +- SD with the predictive band. 4) Move relative RMSE (8.6 % of mean, 5.1 % of 28 d) into the main text. | Revised Figure S6; main-text RMSE sentence | A, 1, 8, 9, 16 | C | Not started | 0
7 | Experimental measurement resolution and cleaning controls | Moderate | User input | 1) Balance model, readability, repeatability, humidity, equilibration. 2) Repeated weighings; stability criterion. 3) Chromic-acid temperature, time, repeated cleaning; blank-control mass change. 4) Specimen-level data table. 5) State plateau 14-28 d is consistent with the data, not demonstrated (Welch p about 0.5; early vs late rates differ). | Methods paragraph; SI table of specimen data | - (your lab records) | D | Not started | 0 | Needs your experimental records; statistics for the plateau sentence already prepared.
8 | Experimental vs computational domain (44 mL vs 27 mL) | Major | Compute + text | 1) Explain domain choice; compare container geometry, specimen position and depth. 2) Domain-size and top-boundary sensitivity on v4 (box 15/30/60, depth). 3) Add optional 48 h medium reset to the code and quantify its effect on Zn2+, pH, O2, film. 4) Explain why renewal is ignored while O2 is replenished. | Sensitivity figure/table in SI; paragraph in Methods | A | B | In progress | 40 | Old-code ablation (box sizes, open O2) exists; must be redone on v4. Update 09-Oct: SI: new section S9 + Figure S10 (disc with no / top+bottom / sides / all O2-replenishing faces; initial O2 1.5-7.5e-9 g/mm3); manuscript limitation sentence on 27 mL vs 44 mL added. Not done: box 15/60 mm, top-boundary level, 48 h reset, v4 re-run of the old ablation.
9 | Continuous O2 replenishment without convection | Major | Compute + text | 1) Sensitivity runs: initial O2, top-boundary O2, liquid depth, sealed vs open, 48 h reset. 2) State that k_ORR is effective and conditional on the assumed O2 history. 3) If possible, measure DO in HBSS. | SI sensitivity table; limitation sentence | A, 8 | B | Draft done | 80 | Ran sealed vs open, directions and also intial O2 conc runs Update 09-Oct: Sealed vs open (None vs All: 0.055 % vs 0.426 % at 672 h) and liquid depth (top+bottom vs sides: 0.424 % vs 0.397 %) interpreted in S9; initial-O2 runs (0.160 / 0.593 / 0.813 % for 1.5 / 5.5 / 7.5 mg/L); source data sheets Supplementary Figure 10a,b added; limitation sentence added (continuous O2 may not reflect 48 h renewal; k_ORR conditional on assumed O2 history). Open: 48 h reset run, HBSS DO measurement, 3.5 mg/L curve missing from the data file, and the panel (a) vs (b) baseline mismatch (0.426 % vs about 0.335 %) must be explained.
10 | Single-phase ZnO film simplification; wording of F/Fmax | Moderate | Compute + text | 1) Use 'film coverage' only for theta (now a true surface variable); remove 'F/Fmax coverage' wording elsewhere. 2) Sensitivity to porosity, tortuosity, density, thickness. 3) Separate O2 depletion by consumption from film blocking (film on vs off runs). 4) Moderate mechanistic claims. | Text edits; SI sensitivity table | A | B | In progress | 20 | Surface-film model implemented; film tests running; thickness delta_f still an assumption (5 um). Update 09-Oct: Decision: manuscript keeps the volumetric film (F, Fmax, D_eff reduction) matching the code now used; theta / delta_f surface-film wording not applied. Film sensitivities not yet run.
11 | Chloride second-order dependence | Moderate | Compute + text | 1) Explain origin of Cl^2 (effective order). 2) Test exponent 1 vs 2 (show only rescales k_d because Cl is uniform). 3) Show chloride field varies little, so Eq. 8 is optional. 4) Say 'mechanistically informed effective model'. | Paragraph + small SI test | A | B | In progress | 10 | Cl^2 confirmed in code; mass-based k_d conversion factor 7.96e8 known. Update 09-Oct: k_d now stated in mm6 g-2 h-1 (Table 2 ranges, SI Table S5, units table S13); exponent test not run.
12 | O2 balance vs Zn loss | Major | Compute + text | Report n_Zn,lost, n_O2,consumed and ratio at 24/168/336/672 h for the final model; explain any deviation. | Table S-B (O2 columns) | A, 2 | B | In progress | 60 | v4: Zn source / O2-stoichiometry 1.03-1.18; v2: 19-21x out. Redo on final model.
13 | Geometry transfer (one stent) and basis of 6-7 % in vivo range | Moderate | Compute + text | 1) Re-run stent on v4 with final parameters. 2) Reword as order-of-magnitude consistency check. 3) Document the in vivo metric (what is measured, how, material, duration). | Stent results; wording; citation details | A | C | Not started | 0 | Stent mesh is 21M tetrahedra; needs large cores. Update 09-Oct: Decision: kinetic parameters re-calibrated on v4, validation and stent runs kept from earlier runs for now. Manuscript/SI must disclose which model and parameters produced each result and remove "no further adjustment" wording if parameters differ (not yet written). One v4 consistency run recommended.
14 | SA:V baseline comparison | Moderate | Text (+ stent run) | 1) Report naive SA:V scaling (12-13 %) against the model (about 6 %). 2) Separate global mass loss, local recession and transition time. | Paragraph + SI table | 13 | C | Not started | 40 | Numbers already worked out (SA:V 38.5x). Update 09-Oct: SA/V appears in SI Table S4 (disc 1.40, stent 53.9 mm-1), Table S12 (16.07 / 24.11 / 48.21 mm-1) and Figure S8; comparison paragraph (naive scaling 12-13 % vs model about 6 %) to go in S7 after Figure S8 - not yet written, definition of the two numbers needed.
15 | Crown-localisation claims need validation / sub-element accuracy | Moderate | Compute + text | 1) Label 13.2x ratio and crown asymmetry as predictions. 2) Moving-interface benchmark and local penetration-convergence study at micrometre scale. 3) Define the measurement points. | SI benchmark figure; text | A, 16 | C | Not started | 5
16 | Time-step and re-initialisation convergence | Major | Compute + text | 1) dt = 0.5, 0.25, 0.125 h; reinitialisation 0.5/1/2 h. 2) Compare mass loss, penetration depth, transition time, solid-volume conservation, crown ratios. | SI convergence table | A | C | Not started | 0 | Calibration uses dt 4 h without reinit; production uses 0.25 h and 1 h reinit - state both.
17 | Damkohler number definition | Moderate | Compute + text | 1) Give an operational definition and the area-weighted threshold. 2) Plot interface-area fraction by regime vs time (disc and stent). 3) Check mesh sensitivity. | SI figure; definition in Methods | A, 13 | C | Draft done | 0
18 | Design-optimisation claims not demonstrated | Moderate | Text (optional FE) | Moderate the design-optimisation wording, or add a small mechanical case (stiffness/stress before and after crown recession). | Edits in abstract/discussion | 13, 15 | D | Draft done | 0

## Summary
Reviewer-response progress
Status | Count
Not started
In progress
Draft done
Waiting on compute
Done
Total comments
Average % done
Update the Status and % done columns on the Tracker sheet; these counts update automatically.

## Order of work
Phase | What | Comments | Why this order
A Freeze the model | Film tests -> film-mode calibration (k_ORR, k_f, k_d) -> mesh correction on v4 -> fix delta_f, rho_film, tau, D values | 1, 5, 10, 11 | Every number and figure downstream depends on the final parameters.
B Analyses on the frozen model | Balance table, O2 balance, Zn2+/pH metrics, domain / O2 / 48 h sensitivities, film sensitivities, chloride exponent, uncertainty | 2, 4, 8, 9, 12 (then 6) | Each reuses the same disc runs; do the balance first because it feeds the text in 2 and 12.
C Heavy runs | Stent on v4, SA:V comparison, time-step / reinit convergence, local-penetration benchmark, Damkohler regime fractions | 13, 14, 15, 16, 17 | Needs large cores and the frozen parameters; run last.
D Text only (can start now) | Velocity-rule derivation and rewrite of S1, experimental details, plateau wording, design-claim moderation, terminology | 3, 7, 18, (4) | No compute; 7 needs your lab records.

## Compute queue
Run set | Model / mesh | Size | Status | Feeds comments
Film-mode calibration, phase 1 (16 round-number points) | v4 surface film, coarse disc, 336 h | 16 x 4 cores, ~25 min each | Running (job 60860656) | 1, 5, 10
Film-mode phases 2 and 3 (EI + local) | same | 16 more runs | Planned | 1, 5
Second BO repeat (different seed) | same | 28 runs | Planned | 5
Fine-mesh correction pairs | v4 film, disc hmin0.25, 336 h | 4-8 x 16 cores | Planned | 1
Mesh convergence at final parameters | L1-L6 + reference | up to 21M tetrahedra | Planned (check cost) | 1
Balance table runs (672 h, VTK every 24 h) | final model, closed and top-open | 2 x 4 cores, ~45 min | Planned | 2, 12
Domain / O2 / depth / 48 h reset sensitivities | final model | about 12 runs | Partly done (boundary variants and initial-O2 runs; box size and 48 h reset pending) | 8, 9
Film parameter and chloride-exponent sensitivities | final model | about 12 runs | Planned | 10, 11
Morris repeat (calibration ranges) | final model | 180 runs x 10 min | Design ready, cancelled for now | 5, 6
Parameter-propagated ensemble | final model | 50-200 runs | Planned | 6
HBSS validation and stent | final model, production meshes | large | Planned | 13, 14, 15, 17
dt / reinit convergence | arc or stent subset | about 10 runs | Planned | 15, 16

## Change log
Date | File | Change | Tracker ID
09-Oct | Manuscript | Eqs 7, 9, 10, 14 in j_ORR molar form; F molar and Fmax = rho_film(1-eps)/M_film; kappa(F) removed; Table 1 concentrations molar; Robin wording replaced | 2, 3
09-Oct | Manuscript | Limitations: 27 mL vs 44 mL domain; continuous O2 replenishment vs 48 h renewal (k_ORR conditional) | 8, 9
09-Oct | Supplementary | Table S5 Morris ranges updated (k_f, k_d, k_ORR, C_O2,0) | 5, 11
09-Oct | Supplementary | Figure S4 rebuilt: normalized parameter trajectories and RMSE surfaces (32 BO evaluations); caption updated | 5
09-Oct | Supplementary | S8: Figure S9 mesh correction (L2 vs L6, factor 1.355846) | 1
09-Oct | Supplementary | New S9 + Figure S10: domain and O2 supply (replenishing faces, sealed vs open, depth, initial O2) | 8, 9
09-Oct | SourceData.xlsx | Figure 4 sweep labels/captions updated to v4 values (data still to be replaced); sheets Supplementary Figure 10a,b added | 5, 9
09-Oct | Not done | Table S14, Table S15, Tables S9/S10, 3.5 mg/L O2 curve, SA:V paragraph, disclosure of earlier validation/stent runs | 1, 2, 5, 9, 13, 14